## Title
TECHNOLOGY QUALIFICATION REGISTER
| Revision | Date: | Prepared by:
| 1 | 2022-08-28 | SDW
ABOUT
This spreadsheet has been created to facilitate the planning and Execution of Technology Qualification Activities as part of the Floating Offshore Wind Centre of Excellence's (FOW CoE) Mooring and Anchoring System Technology Development and Qualification Programme. Whilst the information contained in this spreadsheet has been prepared and collated in good faith, ORE Catapult and TTI-MR make no representation or warranty (express or implied) as to the accuracy or completeness of the information contained herein nor shall we be liable for any loss or damage resultant from reliance on same. The Technology Qualification Framework comprises the following five stages: Stage 1: Requirements Definition The basis for Technology Qualification defines the inputs to the qualification plan and process, namely what the technology is, how it functions, how it is used, how it is expected to perform and what the overall aims/targets of the qualification process are. Stage 2: Technology Assessment Building upon the Requirements Definition, Stage 2 comprises a detailed assessment of the technology and its maturity as well as the principal uncertainties associated with its use, in order to focus the definition of qualification activities in Stage 3. Sheets are provided to carry out a System Breakdown, Technology Maturity Assessment and FMECA. Stage 3: Technology Plan Development The overall aim of Stage 3 is to develop a qualification strategy that address the risks and uncertainties, and hence reduce the likelihood of failure, according to the failure modes identified in Stage 2. Stage 4: Technology Plan Execution The TQ activities specified in the TQ plan are carried out in this Stage, resulting in the collection of documented evidence in the form of data and insights through experience, numerical analyses and tests. Stage 5: Review The final stage of the TQ process comprises an assessment of whether the qualification activities have been implemented as planned, and hence whether the collated evidence satisfies all of the acceptance criteria defined in the TQ plan.
How to use this spreadsheet
Reference to the supporting documentation PN000487-RPT-XXX-FOW Mooring and Anchoring Technology Qualification Framework and Guidance Notes, as developed under FOW COE project PR28 is recommended in the first instance. Each sheet in this spreadsheet has a yellow notes section which describes each column and relevant functionality. The requirements defined in Stage 1 Requirements Definition and system elements defined in Stage 2 System Breakdown are used by the spreadsheet to automatically populate several dropdown lists in the other sheets. Depending on the performance of your computer, there might be a short delay when entering values in the Stage 1 Requirements Definition and Stage 2 System Breakdown sheets.

## Project Information
PROJECT INFORMATION
In this sheet information regarding the technology and qualification team can be added.
Project Name
Technology Name
Description
Project Team

## Stage 1 Requirements Definition
STAGE 1: REQUIREMENTS DEFINITION
The basis for Technology Qualification defines the inputs to the qualification plan and process, namely what the technology is, how it functions, how it is used, how it is expected to perform and what the overall aims/targets of the qualification process are. In this sheet the requirements of the technology are defined for later comparison with the evidence gathered from qualification activities.
I.D. | Requirement Level 1 | ID | Requirement Level 2 | Description |  | Notes
RQ1.1 | Be sufficiently robust | RQ1.1.1 | Provide tensile load path | When connected provide tensile load connection at the required mooring system design load. |  | I.D. [Text entry]: Unique code to assist requirement identification. Requirement Levels 1 and 2 [Text entry]: Primary and secondary level requirements. Level 2 requirements are used in Stage 3 TQP and Stage 5 Review sheets. Description [Text entry]: Additional commentary as required. Note: Merging of cells is not recommended, as this will interfere with background functions used by this spreadsheet.
RQ1.1 | Be sufficiently robust | RQ1.1.2 | Be fatigue resistant | Be fatigue resistance for the required life of the product and system with an appropriate Design Fatigue factor.
Insert new rows above here if required

## Stage 2 System Breakdown
STAGE 2: TECHNOLOGY ASSESSMENT
SYSTEM BREAKDOWN
Building upon the Requirements Definition, Stage 2 comprises a detailed assessment of the technology and its maturity as well as the principal uncertainties associated with its use, in order to focus the definition of qualification activities in Stage 3. In this sheet the technology is decomposed into its respective system levels, and the function of each element is defined.
System | Function | Sub-System | Function | Sub-sub-system / component | Function |  | Notes
Mooring connector | Remotely connect two parts of mooring system for long-term mooring | Connector body | House/support other sub-systems | Mooring line padeye | Provide connection to mooring line |  | System, Sub-System and Sub-sub-system/component [Text entry]: Unique name of each technology element. Function [Text entry]: A description of the principal role(s) of each technology element. Note: Merging of cells is not recommended, as this will interfere with background functions used by this spreadsheet.
Insert new rows above here if required

## Stage 2 Technology Maturity
TABLE 2
STAGE 2: TECHNOLOGY ASSESSMENT | [12 empty] | IML | 0 | Interface not yet identified.
TECHNOLOGY MATURITY ASSESSMENT | [7 empty] | TABLE 1 |  | Degree of Novelty of Technology |  |  |  | 1 | Interface identified with sufficient detail to allow characterisation of the relationship. | TABLE 3
[10 empty] | Proven | Limited Field History | New or Unproven |  | 2 | Some level of specificity to characterise the interaction. | TML | Categorisation
Building upon the Requirements Definition, Stage 2 comprises a detailed assessment of the technology and its maturity as well as the principal uncertainties associated with its use, in order to focus the definition of qualification activities in Stage 3. In this sheet the level of maturity of a technology is then ranked based on its degree of novelty, uniqueness and current scope of application in the sector. | [7 empty] | Application Area | Known | 1 | 2 | 3 |  | 3 | Technology compatibility allowing integration and interaction. | 1 | Proven Technology
[9 empty] | Limited Knowledge | 2 | 3 | 4 |  | 4 | Sufficient detail in the quality and assurance of the integration. | 2 | New Technology Uncertainties
[9 empty] | New | 3 | 4 | 4 |  | 5 | Sufficient control to establish, manage and terminate the integration. | 3 | New Technical Challenges
[14 empty] | 6 | The integrating technologies can accept, translate and structure information for the intended application. | 4 | Demanding New Technical Challenges
[14 empty] | 7 | Integration verified and validated with sufficient detail to be actionable.
[14 empty] | 8 | Integration completed and mission qualified in the system environment.
System | Sub-System | Sub-sub-system / component | Application area | Degree of novelty | TML (initial) | IML | TML (modified) | Categorisation |  | Notes |  |  |  | 9 | Integration mission proven.
Mooring connector | Connector body | Mooring line padeye | Limited Knowledge | Proven | 2 | 5 | 3 | New Technical Challenges |  | System, Sub-System and Sub-sub-system/component [Dropdown list]: Name of each technology element. Application area [Dropdown list]: The level of accumulated experience of the expected operation conditions or environment of interest i.e., if a technology has never been used in a particular environment before there are high levels of uncertainty on how it will perform (i.e., it is 'New'). Conversely, if sufficient evidence exists that a technology has been operated in a particular application then performance uncertainties are likely to be minimal, hence the application area is 'Known'. Degree of novelty [Dropdown list]: The level of novelty of the technology itself. Modifications to one or more technology elements from a 'Known' state are likely to introduce performance and/or reliability uncertainties. In this scenario the novelty can be classified as 'Limited Field History' or 'New or Unproven' depending on the level of analysis and/or experimentation has been conducted to assess the impact of any change(s). TML (initial) [Automatic]: Technology maturity rating on the scale of 1-5 automatically displayed using the criteria in Table 1. IML [Dropdown list]: Selectable integration maturity on the scale of 0-9 based on the descriptions listed in Table 2. IMLs greater than 6 are deemed to be mature and hence do not influence the TML. For this reason the default IML is set as 7. TML (modified) [Automatic]: Technology maturity rating on the scale of 1-5 automatically modified based on the selected IML. The calculation procedure used to account for the potential TML reduction arising from low IMLs has been adapted from the Bureau Veritas Risk Based Qualification of New Technology - Methodological Guidelines NI 525 DT R01 E (2020) and the Lloyds Register Guidance Notes for Technology Qualification (2017). Categorisation [Automatic]: Descriptive uncertainty category based on the technology maturity and integration maturity ratings as well as the criteria in Table 3.
7
7
7
7
7
7
7
7
7
7
7
[6 empty] | 7 |  |  | Insert new rows above here if required

## Stage 2 FMECA
STAGE 2: TECHNOLOGY ASSESSMENT | [10 empty] | TABLE 1: Impact |  |  |  |  | TABLE 2: Likelihood |  |  |  |  | TABLE 3: Risk Priority |  |  | Likelihood |  |  |  |  | TABLE 4: Criticality Category
FAILURE MODES AND EFFECTS CRITICALITY ANALYSIS | [10 empty] | Score | Rating | Meaning | Description |  | Score | Rating | Meaning | Description | Probability (% per annum) |  |  |  | 1 | 2 | 3 | 4 | 5 | Risk Priority |  | Criticality
[11 empty] | 0 |  | None | Impact removed |  | 0 |  | Never | Risk removed | p < 0.01% |  |  |  | L | L/M | M | M/H | H | R <= 4 | Low | Acceptable
Building upon the Requirements Definition, Stage 2 comprises a detailed assessment of the technology and its maturity as well as the principal uncertainties associated with its use, in order to focus the definition of qualification activities in Stage 3. In this sheet the technological threats and failure modes are defined and their associated risk ratings calculated. A Pareto chart is included to identify dominant failure modes. | [10 empty] | 1 | Low | Insignificant impact | Tolerable delays, tolerable reduction in function/performance |  | 1 | Low | Rarely occur | May occur in exceptional circumstances | 0.01% < p < 0.1% | Impact | 1 | L | 1 | 2 | 3 | 4 | 5 | 4 < R <= 9 | Medium | May be acceptable
[11 empty] | 2 | Low/Medium | Minor impact | Some delay, reduced performance or increased cost impacts project |  | 2 | Low/Medium | Unlikely to occur | Conditions exist for this to occur but controls exist and are effective | 0.1% < p < 1% |  | 2 | L/M | 2 | 4 | 6 | 8 | 10 | 9 < R <= 19 | High | Unacceptable
[11 empty] | 3 | Medium | Moderate impact | Delays, considerable impact on performance and cost |  | 3 | Medium | Possibly occur | Occurrence is possible, measures exist to reduce likelihood but may not be fully effective | 1% < p < 10% |  | 3 | M | 3 | 6 | 9 | 12 | 15 | R > 19 | Critical | Requires immediate action
[11 empty] | 4 | Medium/High | Major impact | Significant delays, non-achievement of function/performance |  | 4 | Medium/High | Likely to occur | Measures may or may not exist to reduce likelihood | 10% < p < 50% |  | 4 | M/H | 4 | 8 | 12 | 16 | 20
[11 empty] | 5 | High | Severe impact | May cause aspects to fail |  | 5 | High | Almost certain | Almost certain to occur | p > 50% |  | 5 | H | 5 | 10 | 15 | 20 | 25
I.D. | System | Sub-System | Sub-Sub-System | Failure mode |  | Failure mechanism or cause | Consequence | Initial Risk |  |  | Strategy | Actions for further control | Action by | Information required | Residual Risk
|  |  |  | Category | Failure |  |  | Impact | Likelihood | Risk Priority Number |  |  |  |  | Impact | Likelihood | Risk Priority Number | [7 empty] | Notes
TA1.1 | Mooring connector | Connector body | Mooring line padeye | Materials | Yield | Material yield caused by overloading | Total failure of the connector | 5 | 2 | High | Mitigate | Material Testing | CM | Material testing to determine the minimum break load limits of the materials. In order to determine the working loads limits of the mooring connector which will reduce the likelihood of the material failure due to overloading. | 5 | 1 | Medium | [7 empty] | I.D. [Text entry]: Unique code to assist requirement identification. System, Sub-System and Sub-sub-system/component [Dropdown list]: Name of each technology element. Failure mode [Dropdown list]: Relevant failure mode. Failure mechanism or cause [Text entry]: Description of the circumstance(s) leading to the failure mode occurring. Consequence [Text entry]: The outcome(s) of the failure mode occurring. Initial risk - Impact [Dropdown list]: Impact score between 1-5 based on the definitions in Table 1. Initial risk - Likelihood [Dropdown list]: Likelihood score between 1-5 based on the definitions in Table 2. Rating [Automatic]: Descriptive risk priority rating automatically displayed using the criteria in Tables 3 and 4. Strategy [Dropdown list]: Determined course of action based on the risk assessment, namely Avoid, Transfer, Mitigate or Accept. Actions for further control [Text entry]: Actions to be taken to reduced initial risk. Action by [Text entry]; The initials of the owner of the "Actions for further control". Information required [Text entry]: Additional information to support the "Actions for further control". Residual risk - Impact [Dropdown list]: Impact score between 1-5 based on the "Actions for further control". Residual risk - Likelihood [Dropdown list]: Likelihood score between 1-5 based on the "Actions for further control". Failure Mode [Pareto chart]: Showing the frequency of occurrence of each failure mode to assist in the identification of common priority areas.
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low
[10 empty] | Low | [6 empty] | Low | Insert new rows above here if required

## Stage 3 TQP
STAGE 3: TECHNOLOGY PLAN DEVELOPMENT
The overall aim of Stage 3 is to develop a qualification strategy that address the risks and uncertainties, and hence reduce the likelihood of failure, according to the failure modes identified in Stage 2. In this sheet the qualification activities are defined, which may comprise desk-based and/or experimental studies. Each activity can be defined in terms of the failure mode and requirement it aims to address. A standard title search function is provided to assist with finding relevant M&A standards and guidance documents.
Experimental Qualification Activities | [13 empty] | Notes
I.D. | Failure Mode Category | Failure mode addressed | Relation to requirement | Purpose | Activity | Acceptance | Standard(s) | Limits (for test design) | Parameters | Accuracy | Analysis | Justification |  | I.D. [Text entry]: Unique code to identify each qualification activity. Must have a 'TQA' prefix. Failure mode addressed [Dropdown list]: Failure mode that the test aims to address (if relevant). Relation to requirement [Dropdown list]: Predefined Level 2 requirement that the test aims to address (if relevant). Purpose [Text entry]: Objective of the test. Test [Text entry]: Type of test. Acceptance [Text entry]: Criteria that, if satisfied will satisfy the objectives of the qualification activity. Standards [Text entry]: Standards relevant to the test. The title search facility on the Standard Search sheet (cell: C11) can be used to identify appropriate standards. Limits [Text entry]: Boundaries of the test, e.g., maximum force, temperature etc. Parameters [Text entry]: The principal variables that will be altered in the test, e.g., strain rates etc. Accuracy [Text entry]: The required accuracy of the test which will enable conclusions to be made regarding the test results with an acceptable level of confidence. Analysis [Text entry]: Any subsequent post-processing and/or analysis that may be required. Justification [Text entry]: The rationale for carrying out the test in the context of the purpose of the qualification activity.
TQA1.1 | Materials | Fatigue | Be fatigue resistant | Determine the fatigue life of the mooring connector | Cyclic fatigue testing of the mooring connector at different loads | Creation of an S-N curve for the connector | DNV-RP-C203 - Fatigue Design of Offshore Steel Structures DNV-OS-E302 Offshore mooring chain | Similar environmental conditions to deployment | Load (kN) | +/- 5% | Post-processing of cycles to failure for each load range. | The test will help determine the design life of the mooring connector
Insert new rows above here if required
Other Qualification Activities | [9 empty] | Notes
I.D. | Failure Mode Category | Failure mode addressed | Relation to requirement | Purpose | Activity | Evidence required | Success criteria | Standard(s) |  | I.D. [Text entry]: Unique code to identify each qualification activity. Must have a 'TQA' prefix. Failure mode addressed [Dropdown list]: Failure mode that the activity aims to address (if relevant). Relation to requirement [Dropdown list]: Predefined Level 2 requirement that the activity aims to address (if relevant). Purpose [Text entry]: Objective of the activity. Activity [Text entry]: Type of activity. Evidence required [Text entry]: The key outcome(s) of the activity, typically in the form of documentation and/or data. Success criteria [Text entry]: Criteria that, if satisfied will satisfy the objectives of the qualification activity. Standards [Text entry]: Standards relevant to the activity. The title search facility on the Standard Search sheet (cell: C11) can be used to identify appropriate standards.
TQA01 | Materials | Yield | Provide tensile load path | Determine strength of the mooring connector | Conduct Finite Element Analysis | Finite Element Report detailing max load the mooring could support | Load capability of mooring connector are determined | DNV-OS-E302 Offshore mooring chain
Insert new rows above here if required

## Stage 4 TQE
STAGE 4: TECHNOLOGY PLAN EXECUTION
The TQ activities specified in the TQ plan are carried out in this Stage, resulting in the collection of documented evidence in the form of data and insights through experience, numerical analyses and tests. In this sheet the progress of the activities can be tracked and the evidence produced by the qualification activities logged.
Qualification Activities
I.D. | Activity | Target completion date | Progress | Status | Achievement | Notes
TQA1.1 | Cyclic fatigue testing of the mooring connector at different loads | 2022-06-30 | 80% | In-progress | Late | I.D. [Automatic]: Unique code to identify each qualification activity, populated automatically from the Stage 3 TQP sheet. Activity [Automatic]: Activity name, populated automatically from the Stage 3 TQP sheet. Target completion date [Text entry]: User-entered date in DD/MM/YYYY format. Progress [Text entry]: Activity completion percentage, displayed as a progress bar. Status [Automatic]: Activity status, defined as follows: Open = 0%, 0% < In-progress < 100%, Completed = 100%. Achievement [Automatic]: Achievement status, defined automatically based on the activity status, target completion date and today's date, either Open/in-progress, Late or Completed.
TQA01 | Conduct Finite Element Analysis | 2022-06-17 | 100% | Completed | Completed
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A |  |  | FALSE
#N/A | #N/A
Formulas:
Achievement = IF([Progress]<>"",IF((AND([Target completion date]<TODAY(),[Status]<>"Completed")),"Late",IF((AND(OR([Target completion date]>TODAY(),[Target completion date]=TODAY()),OR([Status]="Open",[Status]="In-progress"))),"Open/in-progress","Completed")),"")

## Stage 5 Review
STAGE 5: REVIEW
The final stage of the TQ process comprises an assessment of whether the qualification activities have been implemented as planned, and hence whether the collated evidence satisfies all of the acceptance criteria defined in the TQ plan In this sheet each qualification activity is assessed to determine if it satisfies the original requirements of the programme.
Qualification Activities
I.D. | Activity | Relation to requirements | Evidence location | Status | Notes
TQA1.1 | Cyclic fatigue testing of the mooring connector at different loads | Be fatigue resistant | Material testing report | Not satisfied | I.D. [Automatic]: Unique code to identify each qualification activity, populated automatically from the Stage 3 TQP sheet. Activity [Automatic]: Activity name, populated automatically from the Stage 3 TQP sheet. Relation to requirements [Dropdown list]: Predefined Level 2 requirement that the test aims to address (if relevant). Evidence location [Text entry]: Location of documentation, e.g., folder, server address, report etc. Status [Dropdown list]: Selectable colour-coded status for each qualification activity.
TQA01 | Conduct Finite Element Analysis | Provide tensile load path | Finite element analysis report | Satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied
#N/A | #N/A |  |  | Not satisfied

## Standard Search
STANDARD SEARCH
Technology Qualification activities are usually carried out in accordance with national and international regulations, standards or guidance developed by Classification Societies or other institutions. This sheet features a simple title search for mooring and anchoring-related standards and guidance.
Standard title search | chain |  | Notes
Society | Title | Date | Standards [Text entry]: The title search facility on this sheet (cell: C11) can be used to identify appropriate standards.
American Bureau of Shipping | Guide for the certification of offshore mooring chain | 2017
American Petroleum Institute | API Spec 2F Specification for mooring chain | 1997
Bureau Veritas | NI 604 Fatigue of top chain of mooring lines due to in-plane and out-of-plane bendings | 2014
ClassNK | Anchor chain cables and accessories including chafing chain for emergency towing arrangements W18 | 2021
Det Norske Veritas | DNV-OS-E302 Offshore mooring chain | 2018
Det Norske Veritas | DNVGL-CP-0237 Offshore mooring chain and accessories | 2018
International Organisation for Standardisation | ISO 1704 Ships and marine technology - Stud-link anchor chains | 2022
International Organisation for Standardisation | ISO 20438:2017 Ships and marine technology — Offshore mooring chains | 2017
Lloyds Register | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope | 2020
Lloyds Register | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope | 2020
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -

## HiddenSheet
Publisher | Title | Year | Category | System | Sub-System | Sub-sub-system / component | Item count |  | Level 2 Requirements | Item count |  | TRL (LR) |  | Failure modes | [6 empty] | Item count |  |  | Frequency | Mode count | Non-zero modes | Non-zero frequency | Minor addition | Rank | Required order | Index | Sorted modes | Respective counts | Response | Progress | Activity achieved | Requirement satisfied | Category | Standards categories | Search results | Abridged list | Search count | TQ activities |  |  | Activity count | TML colours |  | Risk colours |  | IML colours
American Bureau of Shipping | Guidance Notes on Design and Installation of Drag Anchors and Plate Anchors | 2018 | Anchors & Foundations | Mooring connector | Connector body | Mooring line padeye | System | 1 | Provide tensile load path | Requirements | 2 | 0 | New or unproven | Materials | Mechanical | Comms and Control Instrumentation | Fluid power systems | Environmental | Synthetic Rope | Other | Materials | 12 | Brittle Fracture | 0 | 199 | Yield | 1 | 1.0002 | 1 | 1 | 1 | Yield | 1 | Avoid | Open | Open/in-progress | Not satisfied | Technical | Steel fabrications |  | Guide for the certification of offshore mooring chain | 10 | FALSE | TQA1.1 | Cyclic fatigue testing of the mooring connector at different loads | 2 | 1 | #DCFF5A | 0 | #FFFFFF | 0 | #FFFFFF
American Bureau of Shipping | Guidance Notes on Design and Installation of Dynamically Installed Piles | 2018 | Anchors & Foundations | 0 | 0 | 0 | Sub-system | 1 | Be fatigue resistant |  |  | 1 | New or unproven | Brittle Fracture | Abrasive Wear | Ageing | Burst | Biofouling | Break | Design intent not realised | Mechanical | 14 | Corrosion | 0 | [5 empty] | 2 |  |  |  | Transfer | In-progress | Completed | Satisfied | H&S | Floating structure |  | API Spec 2F Specification for mooring chain |  | FALSE | TQA01 | Conduct Finite Element Analysis |  | 2 | #FFD75F | 1 | #DCFF5A | 1 | #ecf8fb
American Bureau of Shipping | Guide for the certification of offshore mooring chain | 2017 | Chain |  |  |  | Component | 1 | 0 |  |  | 2 | New or unproven | Corrosion | Balance | Connectors (mating, malfunction) | Clogging | Foreign Material Ingress | CBOS | Installation/recovery | Comms and Control Instrumentation | 10 | Material Creep | 0 | [5 empty] | 3 |  |  |  | Mitigate | Completed | Late |  |  | Fibre ropes | Guide for the certification of offshore mooring chain | NI 604 Fatigue of top chain of mooring lines due to in-plane and out-of-plane bendings |  | FALSE |  |  |  | 3 | #FF9632 | 2 | #FFD75F | 2 | #daf1f7
American Bureau of Shipping | Guide for Building and Classing Floating Offshore Wind Turbines | 2020 | Classification & Certification | [8 empty] | 3 | Limited field history | Material Creep | Erosion | Electrical insulation degradation | Contamination and Condensation | Ozone | Coating Split | Other | Fluid power systems | 8 | Hydrogen Embrittlement | 0 | [5 empty] | 4 |  |  |  | Accept |  |  |  |  | Anchors |  | Anchor chain cables and accessories including chafing chain for emergency towing arrangements W18 |  | FALSE |  |  |  | 4 | #FF3219 | 3 | #FF9632 | 3 | #c7ebf3
American Bureau of Shipping | ABS Rules for Building and Classing Floating Production Installations | 2014 | Design and Fabrication of Offshore Structures | [8 empty] | 4 | Limited field history | Hydrogen Embrittlement | Caviation | Electro-optical equipment malfunction | Control System Loss | Sediment | Creep |  | Environmental | 7 | Fatigue | 0 | [5 empty] | 5 | [8 empty] | FOWT |  | DNV-OS-E302 Offshore mooring chain |  | FALSE | [5 empty] | 4 | #FF3219 | 4 | #b5e4ef
American Bureau of Shipping | ABS Rules for Building and Classing Mobile Offshore Units | 2022 | Design and Fabrication of Offshore Structures | [8 empty] | 5 | Limited field history | Fatigue | Crushing | High Voltage (Supply) | Hydraulic Lock | Unforseen environmental conditions | Cut |  | Synthetic Rope | 10 | Material Compatibility | 0 | [5 empty] | 6 | [8 empty] | Inspection |  | DNVGL-CP-0237 Offshore mooring chain and accessories |  | FALSE | [5 empty] | 5 | #FF0000 | 5 | #a2ddec
American Bureau of Shipping | ABS Technical Report TR-2010-03, “Polyester Rope Stiffness modeling, Testing, and Analysis”, | 2010 | Fibre Ropes | [8 empty] | 6 | Proven | Material Compatibility | Fretting | Low Voltage (Supply) | Leak | UV | External Abrasion |  | Other | 4 | Material degradation and ageing | 0 | [5 empty] | 7 | [8 empty] | Moorings |  | ISO 1704 Ships and marine technology - Stud-link anchor chains |  | FALSE | [7 empty] | 6 | #90d7e8
American Bureau of Shipping | Guidance notes on the application of fiber rope for offshore mooring | 2021 | Fibre Ropes | [8 empty] | 7 | Proven | Material degradation and ageing | Impact | Short Circuit | Pressure Loss |  | Flex Fatigue |  |  |  | Mechanical properties and temperature | 0 | [5 empty] | 8 | [8 empty] | Chain |  | ISO 20438:2017 Ships and marine technology — Offshore mooring chains |  | FALSE | [7 empty] | 7 | #7dd0e4
American Bureau of Shipping | Guide for Nondestructive Inspection | 2020 | Inspection | [10 empty] | Mechanical properties and temperature | Mating/Inter-facing | Transmission Losses |  |  | Internal Abrasion |  |  |  | Swelling | 0 | [5 empty] | 9 | [8 empty] | Risk analysis |  | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope |  | FALSE | [7 empty] | 8 | #6bc9e0
American Bureau of Shipping | Guide for Position Mooring Systems | 2020 | Mooring Systems | [10 empty] | Swelling | Mechanical Yield | Thermal Expansion |  |  | Strand Pull Out |  |  |  | Yield | 1 | [5 empty] | 10 | [8 empty] | Qualification |  | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope |  | FALSE | [7 empty] | 9 | #59c3dd
American Institute of Steel Construction | AISC American Institute of Steel Construction Specifications for the Design, Fabrication and Erection of Structural Steel Buildings | 2021 | Steel Fabrications | [10 empty] | Yield | Out-of-Plane Bending | [7 empty] | Abrasive Wear | 0 | [5 empty] | 11 | [8 empty] | Fixed offshore structure |  |  |  | FALSE
American Petroleum Institute | API RP 2GEO Geotechnical and Foundation Design Considerations | 2011 | Anchors & Foundations | [11 empty] | Overload | [7 empty] | Balance | 0 | [5 empty] | 12 | [8 empty] | Chain |  |  |  | TRUE
American Petroleum Institute | API Spec 2F Specification for mooring chain | 1997 | Chain | [11 empty] | Thermal Expansion | [7 empty] | Erosion | 0 | [5 empty] | 13 | [8 empty] | Oil equipment | API Spec 2F Specification for mooring chain |  |  | FALSE
American Petroleum Institute | API RP 2A Recommended Practice for Planning, Designing and Constructing Fixed Offshore Platforms | 2019 | Design and Fabrication of Offshore Structures | [11 empty] | Vibration | [7 empty] | Caviation | 0 | [5 empty] | 14 | [8 empty] | Steel wires |  |  |  | FALSE
American Petroleum Institute | API RP 2A-WSD Planning, Designing and Constructing Fixed Offshore Platforms - Working Stress Design | 2014 | Design and Fabrication of Offshore Structures | [19 empty] | Crushing | 0 | [5 empty] | 15 | [8 empty] | Wire rope |  |  |  | FALSE
American Petroleum Institute | API RP 2T Recommended Practice for Planning, Designing and Constructing Tension Leg Platforms | 2010 | Design and Fabrication of Offshore Structures | [19 empty] | Fretting | 0 | [5 empty] | 16 | [8 empty] | Test methods |  |  |  | FALSE
American Petroleum Institute | API RP 2SM Recommended Practice for Design, Manufacture, Installation, and Maintenance of Synthetic Fiber Ropes for Offshore Mooring | 2014 | Fibre Ropes | [19 empty] | Impact | 0 | [5 empty] | 17 | [8 empty] | Plastic fabrications |  |  |  | FALSE
American Petroleum Institute | API RP 2I In-service inspection of mooring hardware for floating structures | 2008 | Inspection | [19 empty] | Mating/Inter-facing | 0 | [5 empty] | 18 | [8 empty] | Soil engineering |  |  |  | FALSE
American Petroleum Institute | API RP 2SK Recommended Practice for Design and Analysis of Station-keeping Systems for Floating Structures | 2008 | Mooring Systems | [19 empty] | Out-of-Plane Bending | 0 | [5 empty] | 19 | [8 empty] | self elevating units |  |  |  | FALSE
American Petroleum Institute | API Spec 6A/ISO 10423 Petroleum and natural gas industries - Drilling and production equipment - Wellhead and christmas tree equipment | 2018 | Oil & Gas Equipment | [19 empty] | Overload | 0 | [5 empty] | 20 | [8 empty] | Concrete structure |  |  |  | FALSE
American Petroleum Institute | API Spec. 16A Specification for Drill Through Equipment | 2017 | Oil & Gas Equipment | [19 empty] | Thermal Expansion | 0 | [5 empty] | 21 | [8 empty] | plated fabrications |  |  |  | FALSE
American Petroleum Institute | API Spec. 17J Specification for Unbonded Flexible Pipe | 2014 | Oil & Gas Equipment | [19 empty] | Vibration | 0 | [5 empty] | 22 | [8 empty] | MRE Tech |  |  |  | FALSE
American Petroleum Institute | API Spec. 17L1 Specification of Flexible Pipe Ancillary Equipment | 2013 | Oil & Gas Equipment | [19 empty] | Ageing | 0 | [5 empty] | 23 | [8 empty] | Hydrodynamics calc |  |  |  | FALSE
American Petroleum Institute | API RP 17Q Recommended Practice on Subsea Equipment Qualification | 2018 | Technology Qualification | [19 empty] | Connectors (mating, malfunction) | 0 | [5 empty] | 24 | [8 empty] | Survey |  |  |  | FALSE
American Petroleum Institute | API RP 17N Recommended Practice on Subsea Production System Reliability, Technical Risk, and Integrity Management | 2017 | Risk Analysis & Management | [19 empty] | Electrical insulation degradation | 0 | [5 empty] | 25 | [8 empty] | Certification Marine units |  |  |  | FALSE
American Petroleum Institute | API Spec 9A / ISO 10425 Steel wire ropes for the petroleum and natural gas industries – Minimum requirements and terms for acceptance | 2020 | Wire rope | [19 empty] | Electro-optical equipment malfunction | 0 | [5 empty] | 26 | [8 empty] | survey steel units |  |  |  | FALSE
American Society for Nondestructive Testing | ASNT SNT-TC-1A American Society for Non-destructive Testing – Recommended Practice | 2016 | Test Methods | [19 empty] | High Voltage (Supply) | 0 | [5 empty] | 27 | [8 empty] | Offshore classification |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D1248 Standard Specification for Polyethylene Plastics Moulding and Extrusion Materials | 2016 | Plastics | [19 empty] | Low Voltage (Supply) | 0 | [5 empty] | 28 | [8 empty] | Steel ship classification |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D2487 - 11 Standard Practice for Classification of Soils for Engineering Purposes (Unified Soil Classifica_x0002_tion System) | 2017 | Geotechnincal Engineering | [19 empty] | Short Circuit | 0 | [5 empty] | 29 | [8 empty] | Lifting |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D3213 - 08 Standard Practices for Handling, Storing, and Preparing Soft Intact Marine Soil | 2019 | Geotechnincal Engineering | [19 empty] | Transmission Losses | 0 | [5 empty] | 30 | [8 empty] | Coating |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D4220 - 95 Standard Practices for Preserving and Transporting Soil Samples. | 2014 | Geotechnincal Engineering | [19 empty] | Thermal Expansion | 0 | [5 empty] | 31 | [8 empty] | sub contractors |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A255 Standard Test Methods for Determining Hardenability of Steel | 2020 | Steel Testing and Analysis | [19 empty] | Burst | 0 | [5 empty] | 32 | [8 empty] | Hull constructions |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A275 Standard Practice for Magnetic Particle Examination of Steel Forgings | 2018 | Steel Testing and Analysis | [19 empty] | Clogging | 0 | [5 empty] | 33 | [8 empty] | Tensioning |  |  |  | TRUE
American Society for Testing and Materials International | ASTM A388 Standard Practice for Ultrasonic Examination of Heavy Steel Forgings | 2019 | Steel Testing and Analysis | [19 empty] | Contamination and Condensation | 0 | [5 empty] | 34 | [8 empty] | 0 |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A487M Specification for Steel Castings suitable for Pressure service | 2021 | Steel Testing and Analysis | [19 empty] | Control System Loss | 0 | [5 empty] | 35 | [8 empty] | Marine equipment |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A488 Practice for Steel Castings, Welding, Qualifications of Procedures and Personnel | 2018 | Steel Fabrications | [19 empty] | Hydraulic Lock | 0 | [5 empty] | 36 | [8 empty] | Maritime services |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A609 Standard Practise for Castings, Carbon, Low-Alloy and Martensitic Stainless Steel, Ultrasonic Examination Thereof | 2018 | Steel Fabrications | [19 empty] | Leak | 0 | [5 empty] | 37 | [8 empty] | Ships |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A703 Steel Castings, General Requirements for Pressure – Containing Parts | 2020 | Steel Fabrications | [19 empty] | Pressure Loss | 0 | [5 empty] | 38 | [8 empty] | Suppliers |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A991 Standard Test Method for Conducting Temperature Uniformity Surveys of Furnaces Used to Heat Treat Steel Products | 2017 | Steel Testing and Analysis | [19 empty] | Biofouling | 0 | [5 empty] | 39 | [8 empty] | Integrity |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D 4751 – 04: Standard Test Method for Determining Apparent Opening Size of a Geotextile, | 2021 | Test Methods | [19 empty] | Foreign Material Ingress | 0 | [5 empty] | 40 | [8 empty] | Umbilicals |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D 885, Standard test methods for tire cords, tire cord fabrics, and industrial filament yarns made from manufactured organic-base fibers | 2014 | Test Methods | [19 empty] | Ozone | 0 | [5 empty] | 41 | [8 empty] | Shells |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D2259 Standard Practice for Sampling Yarn for Testing | 2021 | Test Methods | [19 empty] | Sediment | 0 | [5 empty] | 42 | [8 empty] | FEA |  |  |  | FALSE
American Society for Testing and Materials International | ASTM D6611 Standard test method for wet and dry yarn-on-yarn abrasion resistance | 2016 | Test Methods | [19 empty] | Unforeseen environmental conditions | 0 | [5 empty] | 43 | [8 empty] | pipelines |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E 165 Standard Test Method for Liquid Penetrant Examination | 2018 | Test Methods | [19 empty] | UV | 0 | [5 empty] | 44 | [8 empty] | Marine operations |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E 709 Standard Guide for Magnetic Particle Examination | 2021 | Test Methods | [19 empty] | Break | 0 | [5 empty] | 45 | [8 empty] | Wind turbines |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E112 Test methods for determining average grain size | 2013 | Test Methods | [19 empty] | CBOS | 0 | [5 empty] | 46 | [8 empty] | composite |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E1417 Standard Practice for Liquid Penetrant Examination | 2021 | Test Methods | [19 empty] | Coating Split | 0 | [5 empty] | 47 | [8 empty] | steel structures |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E1444 Standard Practice for Magnetic Particle Testing | 2021 | Test Methods | [19 empty] | Creep | 0 | [5 empty] | 48 | [8 empty] | Offshore units |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E381 Method of Macro-etch Testing Steel Bars, Billets, Blooms and Forgings | 2020 | Test Methods | [19 empty] | Cut | 0 | [5 empty] | 49 | [8 empty] | Electrical equipment |  |  |  | FALSE
American Society for Testing and Materials International | ASTM E587 Practice for Ultrasonic Angle-Beam Examination by the Contact Method | 2020 | Test Methods | [19 empty] | External Abrasion | 0 | [5 empty] | 50 | [8 empty] | Environment |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A586 Zinc Coated Parallel and Helical Structural Strand and Zinc Coated Wire for Spun-in-Place Structural Strand | 2018 | Wire rope | [19 empty] | Flex Fatigue | 0 | [5 empty] | 51 | [8 empty] | test procedure |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A603 Standard Specification for Zinc-Coated Steel Structural Wire Rope | 2019 | Wire rope | [19 empty] | Internal Abrasion | 0 | [5 empty] | 52 | [8 empty] | Raw material |  |  |  | FALSE
American Society for Testing and Materials International | ASTM A856 Standard Specification for Zinc-5% Aluminium-Mischmetal Alloy-Coated Carbon Steel Wire | 2014 | Wire rope | [19 empty] | Strand Pull Out | 0 | [5 empty] | 53 | [8 empty] | Concrete structures |  |  |  | FALSE
American Society of Mechanical Engineers | ANSI/ASME B16.5 Pipe Flanges and Flanged Fittings | 1996 | Oil & Gas Equipment | [19 empty] | Design intent not realised | 0 | [5 empty] | 54 | [8 empty] | Towing |  |  |  | FALSE
American Society of Mechanical Engineers | ASME IX Welding and Brazing Qualifications | 2013 | Training | [19 empty] | Installation/recovery | 0 | [5 empty] | 55 | [8 empty] | Machine |  |  |  | FALSE
American Welding Society | AWS D1.1 Structural Welding Code - Steel | 2020 | Welding | [19 empty] | Other | 0 | [5 empty] | 56 | [8 empty] | weldings |  |  |  | FALSE
British Standard | BS 5760, Part 5, Guide to failure modes, effects and criticality analysis | 2014 | Risk Analysis & Management | [19 empty] | Mechanical Yield | 0 | [5 empty] | 57 | [8 empty] | Space |  |  |  | FALSE
British Standard | BS 7910 Guide on methods for assessing the acceptability of flaws in fusion welded structures | 2019 | Steel Testing and Analysis | [19 empty] | TestFM | 0 | [5 empty] | 58 | [8 empty] | chains |  |  |  | FALSE
BSH | BSH Standard for Geotechnical Site and Route Surveys - Minimum Requirements for the Foundation of Offshore Wind Turbines and Power Cable Route Burial Assessments | 2014 | Geotechnincal Engineering | [20 empty] | 0 | [5 empty] | 59 | [8 empty] | Metocean |  |  |  | FALSE
BSH | BSH Standard Ground Investigation for Offshore Wind Farms | 2008 | Geotechnincal Engineering | [20 empty] | 0 | [5 empty] | 60 | [8 empty] | Installation |  |  |  | FALSE
Bureau Veritas | NI 604 Fatigue of top chain of mooring lines due to in-plane and out-of-plane bendings | 2014 | Chain | [20 empty] | 0 | [5 empty] | 61 | [8 empty] | Yarns | NI 604 Fatigue of top chain of mooring lines due to in-plane and out-of-plane bendings |  |  | FALSE
Bureau Veritas | NR320 Certification Scheme of Materials and Equipment for the Classification of Marine Units | 2018 | Classification & Certification | [20 empty] | 0 | [5 empty] | 62 | [8 empty] | Plastics |  |  |  | FALSE
Bureau Veritas | NR445, Rules for the Classification of Offshore Units | 2019 | Classification & Certification | [20 empty] | 0 | [5 empty] | 63 | [8 empty] | steel fasteners |  |  |  | FALSE
Bureau Veritas | NR467 Rules for the Classification of Steel Ships | 2022 | Classification & Certification | [20 empty] | 0 | [5 empty] | 64 | [8 empty] | software development |  |  |  | FALSE
Bureau Veritas | NR595 Classification of offshore handling systems | 2014 | Classification & Certification | [20 empty] | 0 | [5 empty] | 65 | [8 empty] | Material selection |  |  |  | FALSE
Bureau Veritas | NR494 Rules for the Classification of Offshore Loading and Offloading Buoys | 2006 | Classification & Certification | [20 empty] | 0 | [5 empty] | 66 | [8 empty] | Environment impact on floating structure |  |  |  | FALSE
Bureau Veritas | NR571 Rules for the classification of column stabilized units | 2016 | Classification & Certification | [20 empty] | 0 | [5 empty] | 67 | [12 empty] | FALSE
Bureau Veritas | NR578 Rules for the classification of tension leg platform | 2012 | Classification & Certification | [20 empty] | 0 | [5 empty] | 68 | [12 empty] | FALSE
Bureau Veritas | NI 631 Certification scheme for Marine Renewable Energy technologies | 2016 | Classification & Certification | [20 empty] | 0 | [5 empty] | 69 | [12 empty] | FALSE
Bureau Veritas | NR530 Coating performance standard | 2013 | Coatings | [20 empty] | 0 | [5 empty] | 70 | [12 empty] | FALSE
Bureau Veritas | NI 594 Design and construction of offshore concrete structures | 2017 | Concrete Structures | [20 empty] | 0 | [5 empty] | 71 | [12 empty] | FALSE
Bureau Veritas | NI 572 DT R02 E Classification and Certification of Floating Offshore Wind Turbines | 2019 | Design and Fabrication of FOWTs | [20 empty] | 0 | [5 empty] | 72 | [12 empty] | FALSE
Bureau Veritas | NI 638 Guidance for Long-term Hydro-structure Calculations | 2019 | Environmental Loads | [20 empty] | 0 | [5 empty] | 73 | [12 empty] | FALSE
Bureau Veritas | NI 432 Certification of fiber ropes for deepwater offshore services | 2018 | Fibre Ropes | [20 empty] | 0 | [5 empty] | 74 | [12 empty] | FALSE
Bureau Veritas | NI 658 − Type approval of fibres and yarns for the manufacturing of fibre ropes | 2018 | Fibre Ropes | [20 empty] | 0 | [5 empty] | 75 | [12 empty] | FALSE
Bureau Veritas | NR546 Hull in composite materials and plywood, material approval, design principles, construction and survey | 2021 | Hull Constructions | [20 empty] | 0 | [5 empty] | 76 | [12 empty] | FALSE
Bureau Veritas | NR561 Hull in aluminium alloys, design principles, construction and survey | 2021 | Inspection | [20 empty] | 0 | [5 empty] | 77 | [12 empty] | FALSE
Bureau Veritas | NR600 Hull structure and arrangement for the classification of cargo ships less than 65m and non cargo ships less than 90 m | 2021 | Inspection | [20 empty] | 0 | [5 empty] | 78 | [12 empty] | FALSE
Bureau Veritas | NR266 Requirements for Survey of materials and equipment for the Classification of Ships and Offshore Units | 2019 | Inspection | [20 empty] | 0 | [5 empty] | 79 | [12 empty] | FALSE
Bureau Veritas | NR426 Construction Survey of Steel Structures of Offshore Units and Installations | 2006 | Inspection | [20 empty] | 0 | [5 empty] | 80 | [12 empty] | FALSE
Bureau Veritas | NR526 Rules for the classification of lifting appliances onboard ships and offshore units | 2021 | Lifting | [20 empty] | 0 | [5 empty] | 81 | [12 empty] | FALSE
Bureau Veritas | NR493 − Classification of mooring systems for permanent offshore units | 2021 | Mooring Systems | [20 empty] | 0 | [5 empty] | 82 | [12 empty] | FALSE
Bureau Veritas | NI 615 Buckling assessment of plated structures for offshore units | 2021 | Plated Structures | [20 empty] | 0 | [5 empty] | 83 | [12 empty] | FALSE
Bureau Veritas | NI 525 Risk based qualification of new technology - Methodological guidelines | 2020 | Risk Analysis & Management | [20 empty] | 0 | [5 empty] | 84 | [12 empty] | FALSE
Bureau Veritas | NI 534, Guidance Note for the Classification of Self-Elevating Units | 2016 | Self Elevating Units | [20 empty] | 0 | [5 empty] | 85 | [12 empty] | FALSE
Bureau Veritas | NI 605 Geotechnical and foundation design | 2014 | Geotechnincal Engineering | [20 empty] | 0 | [5 empty] | 86 | [12 empty] | FALSE
Bureau Veritas | NI 423 Corrosion Protection of Steel Offshore Units and Installations | 2006 | Corrosion Protection | [20 empty] | 0 | [5 empty] | 87 | [12 empty] | FALSE
Bureau Veritas | NI 611 Guidelines for fatigue assessment of steel ships and offshore units | 2020 | Steel Testing and Analysis | [20 empty] | 0 | [5 empty] | 88 | [12 empty] | FALSE
Bureau Veritas | NR216 Rules on Materials and Welding for the Classification of Marine Units | 2021 | Welding | [20 empty] | 0 | [5 empty] | 89 | [12 empty] | FALSE
Bureau Veritas | NR426 construction survey of steel structures of offshore units and installations | 2006 | Steel Testing and Analysis | [20 empty] | 0 | [5 empty] | 90 | [12 empty] | FALSE
Bureau Veritas | NR480 Approval of the manufacturing process of metallic materials | 2021 | Steel Fabrications | [20 empty] | 0 | [5 empty] | 91 | [12 empty] | FALSE
Bureau Veritas | NR533 Approval of service suppliers. | 2022 | Suppliers | [20 empty] | 0 | [5 empty] | 92 | [12 empty] | FALSE
ClassNK | Anchoring Equipment A1 | 2020 | Anchors & Foundations | [20 empty] | 0 | [5 empty] | 93 | [12 empty] | FALSE
ClassNK | Anchor chain cables and accessories including chafing chain for emergency towing arrangements W18 | 2021 | Chain | [20 empty] | 0 | [5 empty] | 94 | [9 empty] | Anchor chain cables and accessories including chafing chain for emergency towing arrangements W18 |  |  | FALSE
ClassNK | Guidelines for Offshore Floating Wind Turbine Structures | 2021 | Design and Fabrication of FOWTs | [20 empty] | 0 | [5 empty] | 95 | [12 empty] | FALSE
ClassNK | Gudiance for the approval and type approval of materials and equipment for marine use | 2021 | Marine Equipment | [20 empty] | 0 | [5 empty] | 96 | [12 empty] | FALSE
ClassNK | General design parameters D3 | 2012 | Design and Fabrication of FOWTs | [20 empty] | 0 | [5 empty] | 97 | [12 empty] | FALSE
Cordage Institute | CI 1202 Terminology for fibre rope | 2013 | Fibre Ropes | [20 empty] | 0 | [5 empty] | 98 | [12 empty] | FALSE
Cordage Institute | CI 2001-04 Fibre rope inspection and retirement criteria | 2004 | Fibre Ropes | [20 empty] | 0 | [5 empty] | 99 | [12 empty] | FALSE
Cordage Institute | CI 2003 Fiber properties for cable cordage rope and twine | 2019 | Fibre Ropes | [20 empty] | 0 | [5 empty] | 100 | [12 empty] | FALSE
Cordage Institute | CIB-1.4 Fiber Rope Technical Information Manual | 1997 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Cordage Institute | CIE-1 Splicing Handbook | 1987 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Cordage Institute | Technical Report TR2009 Determination of marine finish on synthetic fiber yarns. | 2000 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Cordage Institute | CI 1500-02 Test Method for Fiber Rope | 2015 | Test Methods | [20 empty] | 0 | [18 empty] | FALSE
Cordage Institute | CI 1503, Test method for yarn-on-yarn abrasion | 2001 | Test Methods | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-E301 Design and installation of fluke anchors | 2021 | Anchors & Foundations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-E302 Design and installation of plate anchors in clay | 2021 | Anchors & Foundations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-E303 Geotechnical design and installation of suction anchors in clay | 2021 | Anchors & Foundations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-E302 Offshore mooring chain | 2018 | Chain | [20 empty] | 0 | [15 empty] | DNV-OS-E302 Offshore mooring chain |  |  | FALSE
Det Norske Veritas | DNVGL-CP-0237 Offshore mooring chain and accessories | 2018 | Chain | [20 empty] | 0 | [15 empty] | DNVGL-CP-0237 Offshore mooring chain and accessories |  |  | FALSE
Det Norske Veritas | DNVGL-SE-0073 Project certification of wind farms according to IEC 61400-22 | 2014 | Classification & Certification | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0074 Type and component certification of wind turbines according to IEC 61400-22 | 2018 | Classification & Certification | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0422 Certification of floating wind turbines (planned published 2018) | 2018 | Classification & Certification | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-C501 Composite components | 2017 | Composites | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-C502 Offshore concrete structures | 2017 | Concrete Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0119 Design of floating wind turbine structures (replacing DNV-OS-J103) | 2018 | Design and Fabrication of FOWTs | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-A101 Safety principles and arrangements | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-C103 Structural design of column stabilised units – LRFD method | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-C105 Structural design of TLPs – LRFD method | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-C106 Structural design of deep draught floating units – LRFD method | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OTG-13 Prediction of air gap for column-stabilized units | 2019 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-C103 Column-stabilised units | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-F205 Global performance analysis of deepwater floating structures | 2021 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RU-OU-0101 Offshore drilling and support units | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RU-OU-0102 Floating production, storage and loading units | 2018 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-D201 Electrical installations | 2017 | Electrical Equipment | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-C205 Environmental conditions and environmental loads | 2021 | Environmental Loads | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OTG-14 Horizontal wave impact loads for column-stabilized units | 2018 | Environmental Loads | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-C208 Determination of structural capacity by non-linear finite element analysis | 2019 | Finite Element Analysis | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-CP-0173 Fibre ropes for designated service | 2018 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-CP-0174 Synthetic fibres for designated service in ropes | 2014 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0056 Certification of rope based deployment and recovery systems for designated service | 2016 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-E407 Rope based deployment and recovery systems for designated service | 2019 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-E303 Offshore fibre ropes | 2018 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-E304 Damage assessment of fibre ropes for offshore moorings | 2019 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-E305 Design, testing and analysis of offshore fibre ropes | 2019 | Fibre Ropes | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RU-HSLC DNV GL rules for classification: High speed and light craft | 2017 | Life Cycle Analysis | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-C301 Stability and watertight integrity | 2017 | Lifting | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0377 Standard for shipboard lifting appliances | 2018 | Lifting | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0378 Standard for offshore and platform lifting appliances | 2016 | Lifting | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-CG-0036 Calculation of gear rating for marine transmissions | 2015 | Marine Equipment | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-D101 Marine and machinery systems and equipment | 2018 | Marine Equipment | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-N103 Modelling and analysis of marine operations | 2017 | Marine Operations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RU-SHIP Pt.6 Ch.3 Navigation, manoeuvring and position keeping | 2019 | Marine Operations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-ST-N001 Sec.11 Sea voyages | 2018 | Marine Operations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-CG-0550 Maritime services - terms and systematics | 2021 | Marine Operations | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-E301 Position mooring | 2018 | Mooring Systems | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-C201 Structural design of offshore units - WSD method | 2015 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-C401 Fabrication and testing of offshore structures | 2021 | Design and Fabrication of Offshore Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F105 Free spanning pipelines | 2021 | Pipelines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F107 Risk assessment of pipeline protection | 2021 | Pipelines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F109 On-bottom stability design of submarine pipelines | 2021 | Pipelines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F114 Pipe-soil interaction for submarine pipelines | 2021 | Plastics | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-F101 Submarine Pipeline Systems | 2021 | Pipelines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-C201 Buckling Strength of Plated Structures | 2010 | Plated Structures | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0160 Technology qualification management and verification | 2021 | Technology Qualification | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-A203 Technology Qualification | 2021 | Technology Qualification | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-N101 Risk management in marine and subsea operations | 2021 | Risk Analysis & Management | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OSS-300 Risk Based Verification | 2017 | Risk Analysis & Management | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-D102 Failure Mode and Effect Analysis (FMEA) of Redundant Systems | 2012 | Risk Analysis & Management | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-C104 Structural design of self-elevating units – LRFD method | 2015 | Self Elevating Units | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-C104 Self-elevating units | 2015 | Ships | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-C202 Buckling strength of shells | 2017 | Shells | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-CG-0129 Fatigue assessment of ship structures | 2015 | Ships | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-C207 Statistical representation of soil data | 2017 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-C212 Offshore soil mechanics and geotechnical engineering | 2019 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-0416 Corrosion protection for wind turbines | 2021 | Steel Testing and Analysis | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-RP-C203 Fatigue design of offshore steel structures | 2021 | Steel Testing and Analysis | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-B101 Metallic materials | 2019 | Materials | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-C101 Design of offshore steel structures, general - LRFD method | 2018 | Steel Fabrications | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-CP-0346 DNV GL approval of manufacturer scheme | 2016 | Suppliers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-D202 Automation, safety and telecommunication systems | 2014 | Telecommunication Systems | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-OS-F201 Dynamic risers | 2010 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-0360 Subsea power cables in shallow water | 2016 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F203 Riser interference | 2019 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F204 Riser fatigue | 2019 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-RP-F401 Electrical power cables in subsea applications | 2017 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0359 Subsea power cables for wind power plants | 2021 | Umbilicals & Risers | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0176 Certification of navigation and aviation aids of offshore wind farms | 2017 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-SE-0190 Project certification of wind power plants | 2020 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0054 Transport and installation of wind power plants | 2017 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0076 Design of electrical installations for wind turbines | 2021 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0126 Support structures for wind turbines | 2018 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0361 Machinery for wind turbines | 2015 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0376 Rotor blades for wind turbines | 2021 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0437 Loads and site conditions for wind turbines | 2016 | Environmental Loads | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-ST-0438 Control and protection systems for wind turbines | 2016 | Wind Turbines | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNV-OS-E304 Offshore mooring steel wire ropes | 2013 | Wire rope | [20 empty] | 0 | [18 empty] | FALSE
Det Norske Veritas | DNVGL-CP-0256 Offshore mooring steel wire ropes and sockets | 2015 | Wire rope | [20 empty] | 0 | [18 empty] | FALSE
Engineering Equipment and Materials Users Association | EEMUA 194 Guidelines for materials selection and corrosion control for subsea oil and gas production equipment | 2012 | Materials | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1992 Eurocode 2: Design of concrete structures | 2004 | Concrete Structures | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 206 Concrete - Specification, performance, production and conformity | 2013 | Concrete Structures | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1179 Zinc and zinc alloys – Primary zinc | 2012 | Materials | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1537 Execution of special geotechnical work – Ground Anchors | 2000 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1997 Eurocode 7: Geotechnical design | 2004 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1997 Eurocode 8: Design of structures for earthquake resistance | 2004 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1997-1 Eurocode 7: Geotechnical Design – Part 1: General rules | 2004 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 1997-2 Eurocode 7: Geotechnical Design – Part 2: Ground investigation and testing | 2004 | Geotechnincal Engineering | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 10016-4 Non-Alloy Steel Rod for Drawing and/or Cold Rolling. Part 4: “Specific Requirements for Rod for Special Applications” | 1995 | Steel Fabrications | [20 empty] | 0 | [18 empty] | FALSE
European Norm Standard | EN 10083-1 Steels for quenching and tempering – Part 1: General delivery conditions | 2006 | Steel Fabrications
European Norm Standard | EN 10088-2 Stainless Steels –Part 2: “Technical Delivery Conditions for Sheet/Plate and Strip of corrosion resistant steels for general purposes”. | 2020 | Steel Fabrications
European Norm Standard | EN 10204 Metallic products – Types of inspection documents | 2004 | Steel Testing and Analysis
European Norm Standard | EN 1993-1 Eurocode 3: Design of steel structures | 2004 | Steel Fabrications
European Norm Standard | EN 287 Approval testing of welders - Fusion welding | 2013 | Welding
European Norm Standard | EN 10160 Ultrasonic Testing of Steel Flat Product of Thickness Equal or Greater than 6 mm (reflection method) | 2000 | Test Methods
European Norm Standard | EN 10228-1/2/3/4 Non-destructive Testing of Steel Forgings | 2016 | Test Methods
European Norm Standard | EN 473 Qualification and Certification of NDT personnel | 2000 | Training
European Norm Standard | EN 59 Method of testing plastics | 2016 | Test Methods
European Norm Standard | EN ISO 22477-5 Geotechnical investigation and testing — Testing of geotechnical structures — Part 5: Testing of grouted anchors | 2018 | Test Methods
European Norm Standard | EN 10218 Steel Wire and Wire products – General: Part 1 “Test Methods” | 2012 | Wire rope
European Norm Standard | EN 10264-2 Steel wire and wire products – Steel wire for ropes – Part 2: Cold drawn non alloyed steel wire for ropes for general applications | 2021 | Wire rope
European Norm Standard | EN 10264-3 Steel wire and wire products – Steel wire for ropes – Part 3: “Round and shaped non alloyed wire for high duty applications”. | 2021 | Wire rope
European Norm Standard | EN 12385-10 Steel wire ropes – Safety – Part 10: “Spiral ropes for general structural applications” | 2003 | Wire rope
International Association of Classification Societies | IACS UR A2 Shipboard Fittings and Associated Hull Structures Associated with Towing and Mooring on Conventional Vessels | 2020 | Towing
International Electrotechnical Commission | IEC 61400-1 Wind Turbines - Design requirements | 2014 | Design and Fabrication of FOWTs
International Electrotechnical Commission | IEC 61400-3 Wind Turbines - Design requirements for offshore wind turbines | 2009 | Design and Fabrication of FOWTs
International Electrotechnical Commission | IEC 61892-6 Mobile and fixed offshore units – Electrical installations – Part 6: Installation | 2019 | Electrical Equipment
International Electrotechnical Commission | IEC TS 62600-4 Marine energy - Wave, tidal and other water current converters - Part 4: Specification for establishing qualification of new technology | 2020 | Technology Qualification
International Electrotechnical Commission | IEC 60812 Failure modes and effects analysis (FMEA and FMECA) | 2018 | Risk Analysis & Management
International Electrotechnical Commission | IEC 61025 Fault Tree Analysis | 2006 | Risk Analysis & Management
International Electrotechnical Commission | IEC 61882 Hazard and operability studies (HAZOP studies) | 2016 | Risk Analysis & Management
International Electrotechnical Commission | IEC 62502 Analysis techniques for dependability – Event tree analysis (ETA) | 2010 | Risk Analysis & Management
International Electrotechnical Commission | IEC/ISO 31010 Risk Management - Risk Assessment techniques | 2019 | Risk Analysis & Management
International Electrotechnical Commission | IEC-60300-9, Part 3: Application guide - Section 9: Risk analysis of technological systems | 1995 | Risk Analysis & Management
International Electrotechnical Commission | IEC 61400-22 Wind Turbines - Conformity testing and certification | 2010 | Technology Qualification
International Maritime Organization | IMO MSC/Circ.1023−MEPC/Circ.392 Guidelines for Formal Safety Assessment | 2002 | Risk Analysis & Management
International Maritime Organization | IMO MSC 267(85) International Code on Intact Stability (IS Code 2008) | 2008 | Stability
International Maritime Organization | IMO A765(8) Guidelines on the safety of towed ships and other floating objects including installations, structures and platforms at sea | 1993 | Towing
International Maritime Organization | IMO MSC/Circ.1175 "Guidance on Shipboard Towing and Mooring Equipment", 24th May 2005. | 2005 | Towing
International Maritime Organization | IMO MSC/Circ.884 Guidelines for safe ocean towing | 2015 | Umbilicals & Risers
International Organisation for Standardisation | ISO 1704 Ships and marine technology - Stud-link anchor chains | 2022 | Chain | [36 empty] | ISO 1704 Ships and marine technology - Stud-link anchor chains
International Organisation for Standardisation | ISO 20438:2017 Ships and marine technology — Offshore mooring chains | 2017 | Chain | [36 empty] | ISO 20438:2017 Ships and marine technology — Offshore mooring chains
International Organisation for Standardisation | ISO 19903 Petroleum and natural gas industries — Fixed concrete offshore structures | 2019 | Concrete Structures
International Organisation for Standardisation | ISO 19900 Petroleum and natural gas industries - General requirements for offshore structures | 2019 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 19901-2 Petroleum and natural gas industries -- Specific requirements for offshore structures -- Part 2: Seismic design procedures and criteria | 2017 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 19904 Petroleum and natural gas industries — Floating offshore structures | 2019 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 19904-1, Petroleum and natural gas industries — Floating offshore structures — Part 1: Monohulls, semi-submersibles and spars | 2019 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 19901 Petroleum and natural gas industries - Specific requirements for offshore structures | 2014 | Environmental Loads
International Organisation for Standardisation | ISO 2307 Fibre ropes — Determination of certain physical and mechanical properties | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO 18692-1 − 2018 − Fibre ropes for offshore station-keeping - Part 1: General specification | 2018 | Fibre Ropes
International Organisation for Standardisation | ISO 18692-2 − 2019 − Fibre ropes for offshore station-keeping - Part 2: Polyester | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO 18692-3 − Fibre ropes for offshore station-keeping - Part 3: High Modulus Polyethylene (HMPE) - (currently ISO TS 14909 − 2011) | 2020 | Fibre Ropes
International Organisation for Standardisation | ISO 1968 Fibre ropes and cordage – vocabulary | 2004 | Fibre Ropes
International Organisation for Standardisation | ISO 2060, Textiles — Yarn from packages — Determination of linear density (mass per unit length) by the skein method | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO 9554:2019, Fibre ropes — General specifications | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO/TS 17920 − 2015 − Fibre ropes for offshore stationkeeping - Aramid | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO/TS 19336 − 2015 − Fibre ropes for offshore stationkeeping - Polyarylate | 2019 | Fibre Ropes
International Organisation for Standardisation | ISO 19905-1 Petroleum and natural gas industries -- Site-specific assessment of mobile offshore units -- Part 1: Jack-ups | 2016 | Lifting
International Organisation for Standardisation | ISO 12100 Safety of Machinery | 2022 | Marine Equipment
International Organisation for Standardisation | ISO 19901-1 Petroleum and natural gas industries - Specific requirements for offshore structures - Part 1: Meteocean design and operating considerations | 2015 | Environmental Loads
International Organisation for Standardisation | ISO 19901-7 Petroleum and natural gas industries - Specific requirements for offshore structures - Part 7: Stationkeeping systems for floating offshore structures and mobile offshore units | 2013 | Mooring Systems
International Organisation for Standardisation | ISO 13628-5 Petroleum and natural gas industries – Design and operation of subsea production systems – Part 5: Subsea umbilicals | 2009 | Oil & Gas Equipment
International Organisation for Standardisation | ISO 604 Plastics – Determination of compressive properties | 2017 | Plastics
International Organisation for Standardisation | ISO 16290 Space System: Definition of Technology Readiness Levels | 2019 | Technology Qualification
International Organisation for Standardisation | ISO 17776 Petroleum and natural gas industries — Offshore production installations — Major accident hazard management during the design of new installations | 2016 | Risk Analysis & Management
International Organisation for Standardisation | ISO/IEC/IEEE 15288:2015 Systems and software engineering — System life cycle processes | 2015 | Life Cycle Analysis
International Organisation for Standardisation | ISO 14688 series Geotechnical investigation and testing -- Identification and classification of soil | 2017 | Geotechnincal Engineering
International Organisation for Standardisation | ISO 14689-1 Geotechnical investigation and testing -- Identification and classification of rock -- Part 1: Identification and description | 2017 | Geotechnincal Engineering
International Organisation for Standardisation | ISO 17892 series Geotechnical investigation and testing -- Laboratory testing of soil | 2018 | Geotechnincal Engineering
International Organisation for Standardisation | ISO 19901-4 Petroleum and natural gas industries -- Specific requirements for offshore structures -- Part 4: Geotechnical and foundation design consideration | 2016 | Geotechnincal Engineering
International Organisation for Standardisation | ISO 19901-8 (under development) Petroleum and natural gas industries -- Specific requirements for offshore structures -- Part 8: Marine soil Investigations | 2014 | Geotechnincal Engineering
International Organisation for Standardisation | ISO 898-1 Mechanical properties of fasteners made of carbon steel and alloy steel – Part 1: Bolts, screws and studs with specified property classes – Coarse thread and fine pinch thread | 2018 | Fasteners
International Organisation for Standardisation | ISO 19902 Petroleum and natural gas industries — Fixed steel offshore structures | 2020 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 2394 Eurocode 3: Design of steel structures | 2010 | Design and Fabrication of Offshore Structures
International Organisation for Standardisation | ISO 4967 Steel – Determination of content of non-metallic inclusions – Micrographic method using standard diagrams | 2020 | Steel Testing and Analysis
International Organisation for Standardisation | ISO 8501-1 Preparation of steel substrates before application of paints and related products - Visual assessment of surface cleanliness - Part 1: Rust grades and preparation grades of uncoated steel substrates and of steel substrates after overall removal of previous coatings | 2007 | Coatings
International Organisation for Standardisation | ISO 2062, “Methods for Determination of Breaking Strength and Extension” | 2020 | Test Methods
International Organisation for Standardisation | ISO 13588 Non-destructive testing of welds - Ultrasonic testing - Use of automated phased array technology | 2019 | Test Methods
International Organisation for Standardisation | ISO 139, Textiles — Standard atmospheres for conditioning and testing | 2019 | Test Methods
International Organisation for Standardisation | ISO 15549 Non-destructive testing – Eddy current testing – General principles | 2019 | Test Methods
International Organisation for Standardisation | ISO 22475 series Geotechnical investigation and testing -- Sampling methods and groundwater measurements | 2021 | Test Methods
International Organisation for Standardisation | ISO 22476 series Geotechnical investigation and testing -- Field testing. | 2012 | Test Methods
International Organisation for Standardisation | ISO 3108 Steel wire rope for general purposes – determination of actual breaking load | 2017 | Test Methods
International Organisation for Standardisation | ISO 3452 Non-destructive Testing – Penetrant inspection/ testing | 2021 | Test Methods
International Organisation for Standardisation | ISO 7500–1, Metallic materials — Verification of static uniaxial testing machines — Part 1: Tension/compression testing machines — Verification and calibration of the force-measuring system | 2018 | Test Methods
International Organisation for Standardisation | ISO 9712 Non-destructive testing - Qualification and certification of NDT personnel | 2021 | Training
International Organisation for Standardisation | ISO 12076:2002 Steel wire ropes -- Determination of the actual modulus of elasticity | 2018 | Test Methods
International Organisation for Standardisation | ISO 3344 Reinforcement products – Determination of moisture content | 2017 | Test Methods
International Organisation for Standardisation | ISO 15614 Specification and approval of welding procedures for metallic materials | 2017 | Welding
International Organisation for Standardisation | ISO 9606 Approval testing of welders - Fusion welding | 2000 | Welding
International Organisation for Standardisation | ISO 10425: Steel wire ropes for the petroleum and natural gas industries - Minimum requirements and terms of acceptance | 2003 | Wire rope
International Organisation for Standardisation | ISO 16120-4 Non alloyed steel wire rod for conversion to wire: Part 4 “Specific requirements for wire rod for special applications” | 2017 | Wire rope
International Organisation for Standardisation | ISO 17558 Socketing procedures for wire ropes – resin socketing | 2006 | Wire rope
International Organisation for Standardisation | ISO 17893 Steel wire ropes – Vocabulary, designation and classification | 2010 | Wire rope
International Organisation for Standardisation | ISO 2232 Round drawn wire for general purpose non-alloy steel wire ropes and for large diameter steel wire ropes - Specifications | 1990 | Wire rope
International Organisation for Standardisation | ISO 2408: Steel wire ropes - Requirements | 2017 | Wire rope
International Organisation for Standardisation | ISO 4346 Steel wire ropes for general purposes – Lubricants – basic requirements | 2017 | Wire rope
Lloyds Register | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope | 2020 | Chain | [36 empty] | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope
Lloyds Register | Materials and Qualification Procedures for Ships Book P Procedures for Approval of Paints and Coatings | 2020 | Coatings
Lloyds Register | Materials and Qualification Procedures for Ships Book B Procedure for Periodic Inspection of Approved Works. | 2020 | Inspection
Lloyds Register | Materials and Qualification Procedures for Ships Book M Procedures for the Approval in accordance with the Materials Quality Scheme | 2020 | Materials
Lloyds Register | Materials and Qualification Procedures for Ships Book K Procedures for Approval of Plastic Materials | 2020 | Plastics
Lloyds Register | Guidance Notes for Certification Through Technology Qualification | 2022 | Technology Qualification
Lloyds Register | Materials and Qualification Procedures for Ships Book L Procedures for Approval of Repair Procedures | 2020 | Repairs
Lloyds Register | Materials and Qualification Procedures for Ships Book C Procedures for Approval of a Works for Steelmaking and Rolled Steel Products | 2020 | Steel Fabrications
Lloyds Register | Materials and Qualification Procedures for Ships Book D Procedures for Approval of a Works for the Manufacture of Steel Castings | 2020 | Steel Fabrications
Lloyds Register | Materials and Qualification Procedures for Ships Book E Procedures for Approval of a Works for the Manufacture of Steel Forgings | 2020 | Steel Fabrications
Lloyds Register | Materials and Qualification Procedures for Ships Book F Procedures for Approval of a Works for the Manufacture of Iron Casting | 2020 | Steel Fabrications
Lloyds Register | Materials and Qualification Procedures for Ships Book N Procedures for Approval of Thickness Measurement Firms, Recognition of Firms for performing NDE and Validation of Advanced NDE Methods | 2020 | Test Methods
Lloyds Register | Materials and Qualification Procedures for Ships Book A Guidelines for Qualification of Welding Procedures, Welders and Weldability. | 2020 | Training
Lloyds Register | Materials and Qualification Procedures for Ships Book J Procedures for Approval of Welding Consumables and Manufacture of Fabricated Steel Sections | 2020 | Welding
Lloyds Register | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope | 2020 | Wire rope | [36 empty] | Materials and Qualification Procedures for Ships Book H Procedures for Approval of a Works or Proving Establishment for Chain Cable or Wire Rope
Lloyds Register | Rules and Regulations for the Classification of Offshore Units, Pt3 Ch10 Positional Mooring System | 2022 | Mooring Systems
Lloyds Register | Rules and Regulations for the Classification of Offshore Units, Pt3 Ch20 Guidelines on the Inspection of Positional Mooring Systems | 2022 | Mooring Systems
Lloyds Register | Rules for the Manufacture, Testing and Certification of Materials, Ch10 Equipment for Mooring and Anchoring | 2022 | Mooring Systems
Lloyds Register | Rules and Regulations for the Classification of Offshore Units, Pt3 Ch14 Foundations | 2022 | Anchors & Foundations
NORSOK Standards | NORSOK N-003 Actions and actions effects | 2017 | Environmental Loads
NORSOK Standards | NORSOK M-001 Material selection | 2014 | Environmental Loads
NORSOK Standards | NORSOK N-001 Integrity of offshore structures | 2021 | Hull Constructions
NORSOK Standards | NORSOK N-006 Assessment of structural integrity for existing offshore load-bearing structures | 2015 | Hull Constructions
NORSOK Standards | NORSOK G-001: Marine Soil Investigation | 2004 | Geotechnincal Engineering
NORSOK Standards | NORSOK N-004 Design of steel structures | 2021 | Design and Fabrication of Offshore Structures
Oil Companies International Marine Forum | Anchoring Systems and Procedures | 2010 | Anchors & Foundations
Oil Companies International Marine Forum | OCIMF Prediction of Wind and Current Loads on VLCCs. 2nd Edition 1994 | 1994 | Environmental Loads
Oil Companies International Marine Forum | Guidelines for the purchasing and testing of SPM hawsers | 2001 | Fibre Ropes
Oil Companies International Marine Forum | Mooring Equipment Guidelines (MEG4) | 2018 | Mooring Systems
Oil Companies International Marine Forum | OCIMF publication "Guidelines for offshore tanker operations" | 2018 | Marine Operations
Oil Companies International Marine Forum | OCIMF publication "Recommendations for Oil and Chemical Tanker Manifolds and Associated Equipment". | 2017 | Marine Operations
Oil Companies International Marine Forum | OCIMF/ICS publication "Ship to Ship Transfer Guide (Petroleum)". | 2013 | Marine Operations
Oil Companies International Marine Forum | OCIMF/ICS/IAPH publication "International Safety Guide for Oil Tankers and Terminals". | 2020 | Marine Operations
Oil Companies International Marine Forum | OCIMF Hawser Test Report, 1982 | 1982 | Test Methods
US Army Corps of Engineers | EM 1110-1-2908 "Rock Foundations", US Army Corps of Engineers (1994). | 1994 | Anchors & Foundations